## Summary
Columbus Verification Status Summary | [27 empty] | 2015-08-05
No. | IP | RTL Designer | Verification Engineer | RTL Sim. | [9 empty] | FPGA |  |  |  | POST Sim. |  |  |  | ASIC |  |  |  | Last Updated |  |  |  | Remark / Coverage Waive
|  |  |  | RTL F1 |  | RTL F2 |  | RTL F3 |  | F1~3 | Cov. SoC (F2,F3) | Cov. S.A (F0,F1) | Done | Cases | Pass | Prog. | Done | Cases | Pass | Prog. | Done | Cases | Pass | Prog. | Done | Date | RTL | FPGA | ASIC
|  |  |  | Cases | Pass | Cases | Pass | Cases | Pass | Prog.
1 | Cortex-M3 | 최호윤 수석 | 조성엽 책임 | 18 | 16 | 7 | 3 | 2 | 0 | 70.37% | 0% | 0% | - | 18 | 10.5 | 58.33% | - | 4 | 0 | 0% | - | 15 | 0 | 0% | - | 2015-08-05 | ? | ? | ? | RTL: POST: FPGA:
2 | HCT | 이원규 선임 | 박재우 책임 | 281 | 61 | 61 | 1 | 243 | 0 | 10.6% | 0% | 0% | - | 234 | 0 | 0% | - | 4 | 0 | 0% | - | 232 | 0 | 0% | - | 2015-08-06 | ? | ? | ? | RTL: POST: FPGA:
3 | FCT | 천동엽 책임 | 조성엽 책임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
4 | Buffer Manager | 지대근 책임 | 조성엽 책임 | 60 | 5 | 26 | 0 | 27 | 0 | 4.425% | 0% | 0% | - | 23 | 0 | 0% | - | 22 | 0 | 0% | - | 23 | 0 | 0% | - | 2015-07-10 | ? | ? | ? | RTL: POST: FPGA:
5 | Search Engine | 김현욱 선임 | 김현욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
6 | MTSE | 김현욱 선임 | 김현욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
7 | System Memory | 김현욱 선임 | 김현욱 선임 | 107 | 95 | 14 | 0 | 14 | 0 | 70.37% | 0% | 0% | - | 5 | 0 | 0% | - | 0 | 0 | - | - | 5 | 0 | 0% | - | 2015-08-06 | ? | ? | ? | RTL: POST: FPGA:
8 | Linked List SE | 안병욱 선임 | 안병욱 선임 | 21 | 0 | 0 | 0 | 1 | 0 | 0% | 0% | 0% | - | 22 | 0 | 0% | - | 5 | 0 | 0% | - | 21 | 0 | 0% | - | 2015-08-06 | ? | ? | ? | RTL: POST: FPGA:
9 | DMA | 안병욱 선임 | 안병욱 선임 | 29 | 28 | 0 | 0 | 34 | 0 | 44.44% | 0% | 0% | - | 26 | 0 | 0% | - | 5 | 0 | 0% | - | 13 | 0 | 0% | - | 2015-07-16 | ? | ? | ? | RTL: POST: FPGA:
10 | Back Bone | 최호윤 수석 | 최호윤 수석 | 4 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-28 | ? | ? | ? | RTL: POST: FPGA:
11 | Analog IP | 양창호 선임 | 양창호 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
12 | SysCtrl: PMU | 김정욱 책임 | 김정욱 책임 | 79 | 79 | 115 | 0 | 115 | 0 | 25.57% | 0% | 0% | - | 61 | 0 | 0% | - | 114 | 0 | 0% | - | 104 | 0 | 0% | - | 2015-08-07 | ? | ? | ? | RTL: POST: FPGA:
13 | RPMB | 안병욱 선임 | 안병욱 선임 | 27 | 25 | 29 | 0 | 1 | 0 | 43.86% | 0% | 0% | - | 18 | 0 | 0% | - | 2 | 0 | 0% | - | 18 | 0 | 0% | - | 2015-06-09 | ? | ? | ? | RTL: POST: FPGA:
14 | Mail Box | 안병욱 선임 | 안병욱 선임 | 28 | 0 | 1 | 0 | 17 | 0 | 0% | 0% | 0% | - | 10 | 0 | 0% | - | 1 | 0 | 0% | - | 8 | 0 | 0% | - | 2015-06-10 | ? | ? | ? | RTL: POST: FPGA:
15 | Timer | 안병욱 선임 | 안병욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
16 | WDT | 안병욱 선임 | 안병욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
17 | UART | 안병욱 선임 | 안병욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
18 | SysCtrl: Clock | 김정욱 책임 | 김정욱 책임 | 17 | 17 | 17 | 0 | 17 | 0 | 33.33% | 0% | 0% | - | 3 | 0 | 0% | - | 17 | 0 | 0% | - | 12 | 0 | 0% | - | 2015-08-07 | ? | ? | ? | RTL: POST: FPGA:
19 | SysCtrl: Reset | 김정욱 책임 | 김정욱 책임 | 15 | 15 | 16 | 0 | 17 | 0 | 31.25% | 0% | 0% | - | 14 | 0 | 0% | - | 18 | 0 | 0% | - | 17 | 0 | 0% | - | 2015-08-07 | ? | ? | ? | RTL: POST: FPGA:
20 | eFuse Controller | 안병욱 선임 | 안병욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
21 | M-PHY | 이현주 선임 | 이현주 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
22 | Nand PHY | 이종용 선임 | 이종용 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
23 | Nand IO | 이종용 선임 | 이종용 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
24 | I/O Mux | 양창호 선임 | 양창호 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-06-09 | ? | ? | ? | RTL: POST: FPGA:
25 | HW Bypass | 양창호 선임 | 양창호 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
- | End to End | ALL | 조성엽 책임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
- | Post-Silicon Validation | ALL | ALL
Sub Average |  |  |  | 26.3846 | 13.1154 | 11 | 0.15385 | 18.7692 | 0 | - | 0% | 0% |  | 16.6923 | 0.40385 | - |  | 7.3846 | 0 | - |  | 18 | 0 | -
Sub Sum |  |  |  | 686 | 341 | 286 | 4 | 488 | 0 | 27.85% | - | - |  | 434 | 10.5 | 2.419% |  | 192 | 0 | 0% |  | 468 | 0 | 0%
RTL & FPGA Total | [13 empty] | 1460 | 355.5 | 24.35%
100%
90%
70%
50%
0%
Formulas:
Last Updated = [1]Summary!$AA7
Note on N31: sycho: FPGA 환경에서의 test vector의 coverage 임
Note on N33: sycho: Cortex-M3는 제외

## StatusHistory
Armstrong Verification Summary History
Date | RTL Sim. | [9 empty] | FPGA |  |  |  | POST Sim. |  |  |  | ASIC
| RTL F1 |  | RTL F2 |  | RTL F3 |  | F1~3 | Cov. SoC (F2,F3) | Cov. S.A (F0,F1) | Done | Cases | Pass | Prog. | Done | Cases | Pass | Prog. | Done | Cases | Pass | Prog. | Done | RTL F1
| Cases | Pass | Cases | Pass | Cases | Pass | Prog. | [15 empty] | Prog.
2015-07-22 | 166 | 74 | 63 | 2 | 81 | 0 | 26.57% | - | - |  | 95 | 9.5 | 10% |  | 34 | 0 | 0% |  | 77 | 0 | 0% |  | 44.58%
2015-07-29 | 376 | 263 | 211 | 2 | 237 | 0 | 31.78% | - | - |  | 195 | 9.5 | 4.872% |  | 188 | 0 | 0% |  | 231 | 0 | 0% |  | 69.95%
2015-08-05 | 376 | 263 | 211 | 3 | 237 | 0 | 32.11% | - | - |  | 195 | 10.5 | 5.385% |  | 188 | 0 | 0% |  | 231 | 0 | 0% |  | 69.95%
2015-08-07 | 686 | 341 | 286 | 4 | 488 | 0 | 27.85% | - | - |  | 434 | 10.5 | 2.419% |  | 192 | 0 | 0% |  | 468 | 0 | 0% |  | 49.71%

## Statistic_Table
No. | IP | Test category
|  | RTL F1 |  |  |  |  | RTL F2 |  |  |  |  | RTL F3 |  |  |  |  | FPGA |  |  |  |  | POST |  |  |  |  | ASIC
|  | Sanity | Function | Comprehensive | Performance & Regression | Specific & Etc. | Sanity | Function | Comprehensive | Performance & Regression | Specific & Etc. | Sanity | Function | Comprehensive | Performance & Regression | Specific & Etc. | Sanity | Function | Comprehensive | Performance & Regression | Specific & Etc. | Sanity | Function | Comprehensive | Performance & Regression | Specific & Etc. | Sanity | Function | Comprehensive | Performance & Regression | Specific & Etc.
1 | Cortex-M3 | 9 | 9 | 0 | 0 | 0 | 1 | 3 | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 14 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 10 | 3 | 0 | 0
2 | HCT | 1 | 243 | 22 | 11 | 4 | 2 | 47 | 0 | 12 | 0 | 4 | 225 | 0 | 12 | 2 | 3 | 204 | 25 | 0 | 2 | 0 | 4 | 0 | 0 | 0 | 1 | 204 | 25 | 0 | 2
3 | FCT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Buffer Manager | 5 | 41 | 14 | 0 | 0 | 5 | 0 | 21 | 0 | 0 | 5 | 0 | 22 | 0 | 0 | 5 | 0 | 18 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 5 | 0 | 18 | 0 | 0
5 | Search Engine | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | MTSE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | System Memory | 0 | 73 | 7 | 12 | 7 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Linked List SE | 4 | 15 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 19 | 0 | 2 | 0 | 2 | 3 | 0 | 0 | 0 | 2 | 19 | 0 | 0 | 0
9 | DMA | 5 | 18 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 22 | 6 | 0 | 0 | 2 | 18 | 6 | 0 | 0 | 2 | 0 | 3 | 0 | 0 | 2 | 5 | 6 | 0 | 0
10 | Back Bone | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Analog IP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | SysCtrl: PMU | 4 | 75 | 0 | 0 | 0 | 4 | 0 | 110 | 0 | 1 | 4 | 0 | 111 | 0 | 0 | 3 | 0 | 58 | 0 | 0 | 4 | 0 | 110 | 0 | 0 | 3 | 0 | 101 | 0 | 0
13 | RPMB | 4 | 11 | 12 | 0 | 0 | 1 | 7 | 19 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 7 | 8 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 7 | 8 | 2 | 0
14 | Mail Box | 4 | 24 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 16 | 0 | 0 | 0 | 1 | 8 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 7 | 0 | 0 | 0
15 | Timer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | WDT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | UART | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | SysCtrl: Clock | 4 | 13 | 0 | 0 | 0 | 4 | 3 | 10 | 0 | 0 | 4 | 3 | 10 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 4 | 3 | 10 | 0 | 0 | 3 | 0 | 9 | 0 | 0
19 | SysCtrl: Reset | 4 | 11 | 0 | 0 | 0 | 4 | 8 | 4 | 0 | 0 | 4 | 8 | 5 | 0 | 0 | 3 | 8 | 3 | 0 | 0 | 4 | 8 | 6 | 0 | 0 | 3 | 8 | 6 | 0 | 0
20 | eFuse Controller | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | M-PHY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Nand PHY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Nand IO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | I/O Mux | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | HW Bypass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | End to End | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 46 | 533 | 62 | 26 | 11 | 22 | 68 | 176 | 14 | 1 | 30 | 276 | 163 | 12 | 2 | 25 | 278 | 119 | 5 | 2 | 18 | 21 | 153 | 0 | 0 | 23 | 260 | 176 | 2 | 2
Whole Total |  | 164 | 1436 | 849 | 59 | 18

## Doc.revision
Document revision history
rev | date | description | author
0.1 | 2014-04-29 | 양식 초안 작성 | 조성엽
0.3 | 2015-06-09 | RTL F1, F2, F3 status 추가 및 Columbus 적용 | 조성엽