## Chart 1 - Graph
Columbus Verification Status Summary | [34 empty] | 2015-05-14
No. | IP | RTL Designer | Verification Engineer | RTL Sim. | [13 empty] | FPGA |  |  |  |  | POST Sim. |  |  |  |  | ASIC |  |  |  |  | Last Updated |  |  |  | Remark / Coverage Waive
|  |  |  | F1 |  | F2 |  | F3 |  | F1~3 | Cov. SoC (F2,F3) | Cov. S.A (F0,F1) | Done |  |  | Prog. |  | Cases | Pass | Prog. |  | Done | Cases | Pass | Prog. | Done |  | Cases | Pass | Prog. |  | Done | Date | RTL | FPGA | ASIC
| IP |  |  | Cases | Pass | Cases | Pass | Cases | Pass | Prog. |  |  |  | RTL Case | RTL Pass | % | RTL | FPGA Case | FPGA Pass | % | FPGA |  | Sim. Case | Sim. Pass |  |  | POST Sim. | ASIC Case | ASIC Pass |  | ASIC
1 | Cortex-M3 | 최호윤 수석 | 조성엽 책임 | 10 | 10 | 12 | 5 | 0 | 0 | - | 0% | 0% | - | 22 | 15 | 68.18% |  | 30 | 26 | 86.67% |  | - | 20 | 10 | 50% | - |  | 20 | 5 | 25% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
2 | HCT | 이원규 선임 | 박재우 책임 | 15 | 5 | 12 | 5 | 0 | 0 | - | 0% | 0% | - | 27 | 10 | 37.04% |  | 40 | 25 | 62.5% |  | - | 30 | 20 | 66.67% | - |  | 30 | 2 | 6.667% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
3 | FCT | 천동엽 책임 | 조성엽 책임 | 20 | 18 | 20 | 15 | 0 | 0 | - | 0% | 0% | - | 40 | 33 | 82.5% |  | 30 | 30 | 100% |  | - | 30 | 25 | 83.33% | - |  | 30 | 3 | 10% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
4 | Buffer Manager | 지대근 책임 | 조성엽 책임 | 15 | 10 | 30 | 20 | 0 | 0 | - | 0% | 0% | - | 45 | 30 | 66.67% |  | 20 | 20 | 100% |  | - | 40 | 30 | 75% | - |  | 30 | 2 | 6.667% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
5 | Search Engine | 김현욱 선임 | 김현욱 선임 | 20 | 16 | 15 | 10 | 0 | 0 | - | 0% | 0% | - | 35 | 26 | 74.29% |  | 20 | 20 | 100% |  | - | 20 | 15 | 75% | - |  | 30 | 2 | 6.667% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
6 | MTSE | 김현욱 선임 | 김현욱 선임 | 15 | 14 | 20 | 15 | 0 | 0 | - | 0% | 0% | - | 35 | 29 | 82.86% |  | 30 | 25 | 83.33% |  | - | 20 | 15 | 75% | - |  | 30 | 4 | 13.33% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
7 | System Memory | 김현욱 선임 | 김현욱 선임 | 10 | 8 | 15 | 12 | 0 | 0 | - | 0% | 0% | - | 25 | 20 | 80% |  | 30 | 20 | 66.67% |  | - | 20 | 20 | 100% | - |  | 20 | 3 | 15% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
8 | Data Buffer | 김현욱 선임 | 김현욱 선임 | 8 | 8 | 18 | 15 | 0 | 0 | - | 0% | 0% | - | 26 | 23 | 88.46% |  | 40 | 35 | 87.5% |  | - | 20 | 18 | 90% | - |  | 20 | 4 | 20% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
9 | DMA | 김현욱 선임 | 김현욱 선임 | 9 | 8 | 30 | 20 | 0 | 0 | - | 0% | 0% | - | 39 | 28 | 71.79% |  | 50 | 40 | 80% |  | - | 20 | 20 | 100% | - |  | 20 | 2 | 10% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
10 | Back Bone | 최호윤 수석 | 최호윤 수석 | 30 | 10 | 30 | 25 | 0 | 0 | - | 0% | 0% | - | 60 | 35 | 58.33% |  | 20 | 20 | 100% |  | - | 20 | 15 | 75% | - |  | 20 | 5 | 25% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
11 | System Controller | 김정욱 책임 | 김정욱 책임 | 20 | 18 | 30 | 22 | 0 | 0 | - | 0% | 0% | - | 50 | 40 | 80% |  | 30 | 15 | 50% |  | - | 35 | 30 | 85.71% | - |  | 15 | 2 | 13.33% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
12 | PMU | 김정욱 책임 | 김정욱 책임 | 15 | 14 | 30 | 25 | 0 | 0 | - | 0% | 0% | - | 45 | 39 | 86.67% |  | 30 | 15 | 50% |  | - | 30 | 25 | 83.33% | - |  | 20 | 5 | 25% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
13 | RPMB | 안병욱 선임 | 안병욱 선임 | 20 | 18 | 35 | 23 | 0 | 0 | - | 0% | 0% | - | 55 | 41 | 74.55% |  | 20 | 20 | 100% |  | - | 30 | 25 | 83.33% | - |  | 25 | 2 | 8% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
14 | Mail Box | 안병욱 선임 | 안병욱 선임 | 30 | 20 | 20 | 18 | 0 | 0 | - | 0% | 0% | - | 50 | 38 | 76% |  | 35 | 30 | 85.71% |  | - | 30 | 24 | 80% | - |  | 25 | 5 | 20% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
15 | Timer | 안병욱 선임 | 안병욱 선임 | 15 | 10 | 20 | 15 | 0 | 0 | - | 0% | 0% | - | 35 | 25 | 71.43% |  | 35 | 30 | 85.71% |  | - | 30 | 28 | 93.33% | - |  | 25 | 10 | 40% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
16 | WDT | 안병욱 선임 | 안병욱 선임 | 18 | 10 | 20 | 16 | 0 | 0 | - | 0% | 0% | - | 38 | 26 | 68.42% |  | 35 | 30 | 85.71% |  | - | 40 | 32 | 80% | - |  | 20 | 2 | 10% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
17 | UART | 안병욱 선임 | 안병욱 선임 | 17 | 15 | 25 | 20 | 0 | 0 | - | 0% | 0% | - | 42 | 35 | 83.33% |  | 25 | 30 | 120% |  | - | 25 | 20 | 80% | - |  | 30 | 2 | 6.667% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
18 | Clock Controller | 김정욱 책임 | 김정욱 책임 | 16 | 15 | 25 | 25 | 0 | 0 | - | 0% | 0% | - | 41 | 40 | 97.56% |  | 25 | 20 | 80% |  | - | 25 | 25 | 100% | - |  | 30 | 5 | 16.67% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
19 | Reset Controller | 김정욱 책임 | 김정욱 책임 | 20 | 13 | 25 | 22 | 0 | 0 | - | 0% | 0% | - | 45 | 35 | 77.78% |  | 25 | 20 | 80% |  | - | 25 | 22 | 88% | - |  | 30 | 8 | 26.67% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
20 | eFuse Controller | 안병욱 선임 | 안병욱 선임 | 21 | 20 | 25 | 22 | 0 | 0 | - | 0% | 0% | - | 46 | 42 | 91.3% |  | 40 | 35 | 87.5% |  | - | 25 | 22 | 88% | - |  | 25 | 9 | 36% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
21 | M-PHY | 이현주 선임 | 이현주 선임 | 25 | 22 | 25 | 23 | 0 | 0 | - | 0% | 0% | - | 50 | 45 | 90% |  | 40 | 30 | 75% |  | - | 25 | 23 | 92% | - |  | 25 | 7 | 28% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
22 | Nand PHY | 이종용 선임 | 이종용 선임 | 20 | 20 | 30 | 25 | 0 | 0 | - | 0% | 0% | - | 50 | 45 | 90% |  | 35 | 30 | 85.71% |  | - | 30 | 30 | 100% | - |  | 30 | 5 | 16.67% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
23 | Nand IO | 이종용 선임 | 이종용 선임 | 30 | 25 | 35 | 30 | 0 | 0 | - | 0% | 0% | - | 65 | 55 | 84.62% |  | 35 | 30 | 85.71% |  | - | 20 | 18 | 90% | - |  | 30 | 8 | 26.67% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
24 | Test Mux | 양창호 선임 | 양창호 선임 | 35 | 30 | 20 | 15 | 0 | 0 | - | 0% | 0% | - | 55 | 45 | 81.82% |  | 20 | 20 | 100% |  | - | 30 | 15 | 50% | - |  | 25 | 2 | 8% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
25 | HW Bypass | 양창호 선임 | 양창호 선임 | 20 | 20 | 25 | 25 | 0 | 0 | - | 0% | 0% | - | 45 | 45 | 100% |  | 25 | 20 | 80% |  | - | 25 | 5 | 20% | - |  | 30 | 2 | 6.667% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
26 | Analog IP | 양창호 선임 | 양창호 선임 | 20 | 18 | 30 | 30 | 0 | 0 | - | 0% | 0% | - | 50 | 48 | 96% |  | 30 | 20 | 66.67% |  | - | 30 | 2 | 6.667% | - |  | 40 | 5 | 12.5% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
27 | GPIO | 양창호 선임 | 양창호 선임 | 20 | 10 | 40 | 35 | 0 | 0 | - | 0% | 0% | - | 60 | 45 | 75% |  | 30 | 20 | 66.67% |  | - | 20 | 3 | 15% | - |  | 50 | 2 | 4% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
- | End to End | ALL | 조성엽 책임 | 10 | 5 | 10 | 0 | 0 | 0 | - | 0% | 0% | - | 20 | 5 | 25% |  | 25 | 15 | 60% |  | - | 25 | 5 | 20% | - |  | 20 | 5 | 25% |  | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
- | Post-Silicon Validation | ALL | ALL
Sub Average |  |  |  | 18.7143 | 14.6429 | 24 | 19.0357 | 0 | 0 |  | 0% | 0% |  | 42.7143 | 33.6786 |  |  | 30.3571 | 24.6786 | - |  |  | 26.4286 | 19.3571 | - |  |  | 26.6071 | 4.2143 | -
Sub Sum |  |  |  | 524 | 410 | 672 | 533 | 0 | 0 | 0% | - | - |  | 1196 | 943 |  |  | 850 | 691 | 81.29% |  |  | 740 | 542 | 73.24% |  |  | 745 | 118 | 15.84%
Total | [17 empty] | 1374 | 691 | 50.29%
100%
90%
70%
50%
0%
Formulas:
Last Updated = [1]Summary!$AA7
70%
80%
60%
10%
Note on N33: sycho: FPGA 환경에서의 test vector의 coverage 임
Note on N35: sycho: Cortex-M3는 제외

## Chart 1 - data
Columbus Verification Status Summary | [29 empty] | 2015-05-14
No. | IP | RTL Designer | Verification Engineer | RTL Sim. | [11 empty] | FPGA |  |  |  | POST Sim. |  |  |  | ASIC |  |  |  | Last Updated |  |  |  | Remark / Coverage Waive
|  |  |  | F1 |  | F2 |  | F3 |  | F1~3 | Cov. SoC (F2,F3) | Cov. S.A (F0,F1) | Done |  |  | Cases | Pass | Prog. | Done | Cases | Pass | Prog. | Done | Cases | Pass | Prog. | Done | Date | RTL | FPGA | ASIC
| IP |  |  | Cases | Pass | Cases | Pass | Cases | Pass | Prog. |  |  |  | RTL Case | RTL Pass | FPGA Case | FPGA Pass |  |  | Sim. Case | Sim. Pass |  |  | ASIC Case | ASIC Pass
1 | Cortex-M3 | 최호윤 수석 | 조성엽 책임 | 10 | 10 | 12 | 5 | 0 | 0 | - | 0% | 0% | - | 22 | 15 | 30 | 26 | - | - | 20 | 10 | - | - | 20 | 5 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
2 | HCT | 이원규 선임 | 박재우 책임 | 15 | 5 | 12 | 5 | 0 | 0 | - | 0% | 0% | - | 27 | 10 | 40 | 25 | - | - | 30 | 20 | - | - | 30 | 2 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
3 | FCT | 천동엽 책임 | 조성엽 책임 | 20 | 18 | 20 | 15 | 0 | 0 | - | 0% | 0% | - | 40 | 33 | 30 | 30 | - | - | 30 | 25 | - | - | 30 | 3 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
4 | Buffer Manager | 지대근 책임 | 조성엽 책임 | 15 | 10 | 30 | 20 | 0 | 0 | - | 0% | 0% | - | 45 | 30 | 20 | 20 | - | - | 40 | 30 | - | - | 30 | 2 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
5 | Search Engine | 김현욱 선임 | 김현욱 선임 | 20 | 16 | 15 | 10 | 0 | 0 | - | 0% | 0% | - | 35 | 26 | 20 | 20 | - | - | 20 | 15 | - | - | 30 | 2 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
6 | MTSE | 김현욱 선임 | 김현욱 선임 | 15 | 14 | 20 | 15 | 0 | 0 | - | 0% | 0% | - | 35 | 29 | 30 | 25 | - | - | 20 | 15 | - | - | 30 | 4 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
7 | System Memory | 김현욱 선임 | 김현욱 선임 | 10 | 8 | 15 | 12 | 0 | 0 | - | 0% | 0% | - | 25 | 20 | 30 | 20 | - | - | 20 | 20 | - | - | 20 | 3 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
8 | Data Buffer | 김현욱 선임 | 김현욱 선임 | 8 | 8 | 18 | 15 | 0 | 0 | - | 0% | 0% | - | 26 | 23 | 40 | 35 | - | - | 20 | 18 | - | - | 20 | 4 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
9 | DMA | 김현욱 선임 | 김현욱 선임 | 9 | 8 | 30 | 20 | 0 | 0 | - | 0% | 0% | - | 39 | 28 | 50 | 40 | - | - | 20 | 20 | - | - | 20 | 2 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
10 | Back Bone | 최호윤 수석 | 최호윤 수석 | 30 | 10 | 30 | 25 | 0 | 0 | - | 0% | 0% | - | 60 | 35 | 20 | 20 | - | - | 20 | 15 | - | - | 20 | 5 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
11 | System Controller | 김정욱 책임 | 김정욱 책임 | 20 | 18 | 30 | 22 | 0 | 0 | - | 0% | 0% | - | 50 | 40 | 30 | 15 | - | - | 35 | 30 | - | - | 15 | 2 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
12 | PMU | 김정욱 책임 | 김정욱 책임 | 15 | 14 | 30 | 25 | 0 | 0 | - | 0% | 0% | - | 45 | 39 | 30 | 15 | - | - | 30 | 25 | - | - | 20 | 5 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
13 | RPMB | 안병욱 선임 | 안병욱 선임 | 20 | 18 | 35 | 23 | 0 | 0 | - | 0% | 0% | - | 55 | 41 | 20 | 20 | - | - | 30 | 25 | - | - | 25 | 2 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
14 | Mail Box | 안병욱 선임 | 안병욱 선임 | 30 | 20 | 20 | 18 | 0 | 0 | - | 0% | 0% | - | 50 | 38 | 35 | 30 | - | - | 30 | 24 | - | - | 25 | 5 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
15 | Timer | 안병욱 선임 | 안병욱 선임 | 15 | 10 | 20 | 15 | 0 | 0 | - | 0% | 0% | - | 35 | 25 | 35 | 30 | - | - | 30 | 28 | - | - | 25 | 10 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
16 | WDT | 안병욱 선임 | 안병욱 선임 | 18 | 10 | 20 | 16 | 0 | 0 | - | 0% | 0% | - | 38 | 26 | 35 | 30 | - | - | 40 | 32 | - | - | 20 | 2 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
17 | UART | 안병욱 선임 | 안병욱 선임 | 17 | 15 | 25 | 20 | 0 | 0 | - | 0% | 0% | - | 42 | 35 | 25 | 30 | - | - | 25 | 20 | - | - | 30 | 2 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
18 | Clock Controller | 김정욱 책임 | 김정욱 책임 | 16 | 15 | 25 | 25 | 0 | 0 | - | 0% | 0% | - | 41 | 40 | 25 | 20 | - | - | 25 | 25 | - | - | 30 | 5 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
19 | Reset Controller | 김정욱 책임 | 김정욱 책임 | 20 | 13 | 25 | 22 | 0 | 0 | - | 0% | 0% | - | 45 | 35 | 25 | 20 | - | - | 25 | 22 | - | - | 30 | 8 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
20 | eFuse Controller | 안병욱 선임 | 안병욱 선임 | 21 | 20 | 25 | 22 | 0 | 0 | - | 0% | 0% | - | 46 | 42 | 40 | 35 | - | - | 25 | 22 | - | - | 25 | 9 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
21 | M-PHY | 이현주 선임 | 이현주 선임 | 25 | 22 | 25 | 23 | 0 | 0 | - | 0% | 0% | - | 50 | 45 | 40 | 30 | - | - | 25 | 23 | - | - | 25 | 7 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
22 | Nand PHY | 이종용 선임 | 이종용 선임 | 20 | 20 | 30 | 25 | 0 | 0 | - | 0% | 0% | - | 50 | 45 | 35 | 30 | - | - | 30 | 30 | - | - | 30 | 5 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
23 | Nand IO | 이종용 선임 | 이종용 선임 | 30 | 25 | 35 | 30 | 0 | 0 | - | 0% | 0% | - | 65 | 55 | 35 | 30 | - | - | 20 | 18 | - | - | 30 | 8 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
24 | Test Mux | 양창호 선임 | 양창호 선임 | 35 | 30 | 20 | 15 | 0 | 0 | - | 0% | 0% | - | 55 | 45 | 20 | 20 | - | - | 30 | 15 | - | - | 25 | 2 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
25 | HW Bypass | 양창호 선임 | 양창호 선임 | 20 | 20 | 25 | 25 | 0 | 0 | - | 0% | 0% | - | 45 | 45 | 25 | 20 | - | - | 25 | 5 | - | - | 30 | 2 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
26 | Analog IP | 양창호 선임 | 양창호 선임 | 20 | 18 | 30 | 30 | 0 | 0 | - | 0% | 0% | - | 50 | 48 | 30 | 20 | - | - | 30 | 2 | - | - | 40 | 5 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
27 | GPIO | 양창호 선임 | 양창호 선임 | 20 | 10 | 40 | 35 | 0 | 0 | - | 0% | 0% | - | 60 | 45 | 30 | 20 | - | - | 20 | 3 | - | - | 50 | 2 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
- | End to End | ALL | 조성엽 책임 | 10 | 5 | 10 | 0 | 0 | 0 | - | 0% | 0% | - | 20 | 5 | 25 | 15 | - | - | 25 | 5 | - | - | 20 | 5 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
- | Post-Silicon Validation | ALL | ALL
Sub Average |  |  |  | 18.7143 | 14.6429 | 24 | 19.0357 | 0 | 0 |  | 0% | 0% |  | 42.7143 | 33.6786 | 30.3571 | 24.6786 | - |  | 26.4286 | 19.3571 | - |  | 26.6071 | 4.2143 | -
Sub Sum |  |  |  | 524 | 410 | 672 | 533 | 0 | 0 | 0% | - | - |  | 1196 | 943 | 850 | 691 | 81.29% |  | 740 | 542 | 73.24% |  | 745 | 118 | 15.84%
Total | [15 empty] | 1374 | 691 | 50.29%
100%
90%
70%
50%
0%
Formulas:
Last Updated = [1]Summary!$AA7
Note on N33: sycho: FPGA 환경에서의 test vector의 coverage 임
Note on N35: sycho: Cortex-M3는 제외

## Chart 1 - Graph (2)
Columbus Verification Status Summary | [30 empty] | 2015-05-14
No. | IP | RTL Designer | Verification Engineer | RTL Sim. | [12 empty] | FPGA |  |  |  | POST Sim. |  |  |  | ASIC |  |  |  | Last Updated |  |  |  | Remark / Coverage Waive
|  |  |  | F1 |  | F2 |  | F3 |  | F1~3 | Cov. SoC (F2,F3) | Cov. S.A (F0,F1) | Done |  |  | Prog. | Cases | Pass | Prog. | Done | Cases | Pass | Prog. | Done | Cases | Pass | Prog. | Done | Date | RTL | FPGA | ASIC
| IP |  |  | Cases | Pass | Cases | Pass | Cases | Pass | Prog. |  |  |  | RTL Case | RTL Pass | % | FPGA Case | FPGA Pass | % |  | Sim. Case | Sim. Pass |  |  | ASIC Case | ASIC Pass
1 | Cortex-M3 | 최호윤 수석 | 조성엽 책임 | 10 | 10 | 12 | 5 | 0 | 0 | - | 0% | 0% | - | 22 | 15 | 68.18% | 30 | 26 | 86.67% | - | 20 | 10 | 50% | - | 20 | 5 | 25% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
2 | HCT | 이원규 선임 | 박재우 책임 | 15 | 5 | 12 | 5 | 0 | 0 | - | 0% | 0% | - | 27 | 10 | 37.04% | 40 | 25 | 62.5% | - | 30 | 20 | 66.67% | - | 30 | 2 | 6.667% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
3 | FCT | 천동엽 책임 | 조성엽 책임 | 20 | 18 | 20 | 15 | 0 | 0 | - | 0% | 0% | - | 40 | 33 | 82.5% | 30 | 30 | 100% | - | 30 | 25 | 83.33% | - | 30 | 3 | 10% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
4 | Buffer Manager | 지대근 책임 | 조성엽 책임 | 15 | 10 | 30 | 20 | 0 | 0 | - | 0% | 0% | - | 45 | 30 | 66.67% | 20 | 20 | 100% | - | 40 | 30 | 75% | - | 30 | 2 | 6.667% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
5 | Search Engine | 김현욱 선임 | 김현욱 선임 | 20 | 16 | 15 | 10 | 0 | 0 | - | 0% | 0% | - | 35 | 26 | 74.29% | 20 | 20 | 100% | - | 20 | 15 | 75% | - | 30 | 2 | 6.667% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
6 | MTSE | 김현욱 선임 | 김현욱 선임 | 15 | 14 | 20 | 15 | 0 | 0 | - | 0% | 0% | - | 35 | 29 | 82.86% | 30 | 25 | 83.33% | - | 20 | 15 | 75% | - | 30 | 4 | 13.33% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
7 | System Memory | 김현욱 선임 | 김현욱 선임 | 10 | 8 | 15 | 12 | 0 | 0 | - | 0% | 0% | - | 25 | 20 | 80% | 30 | 20 | 66.67% | - | 20 | 20 | 100% | - | 20 | 3 | 15% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
8 | Data Buffer | 김현욱 선임 | 김현욱 선임 | 8 | 8 | 18 | 15 | 0 | 0 | - | 0% | 0% | - | 26 | 23 | 88.46% | 40 | 35 | 87.5% | - | 20 | 18 | 90% | - | 20 | 4 | 20% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
9 | DMA | 김현욱 선임 | 김현욱 선임 | 9 | 8 | 30 | 20 | 0 | 0 | - | 0% | 0% | - | 39 | 28 | 71.79% | 50 | 40 | 80% | - | 20 | 20 | 100% | - | 20 | 2 | 10% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
10 | Back Bone | 최호윤 수석 | 최호윤 수석 | 30 | 10 | 30 | 25 | 0 | 0 | - | 0% | 0% | - | 60 | 35 | 58.33% | 20 | 20 | 100% | - | 20 | 15 | 75% | - | 20 | 5 | 25% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
11 | System Controller | 김정욱 책임 | 김정욱 책임 | 20 | 18 | 30 | 22 | 0 | 0 | - | 0% | 0% | - | 50 | 40 | 80% | 30 | 15 | 50% | - | 35 | 30 | 85.71% | - | 15 | 2 | 13.33% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
12 | PMU | 김정욱 책임 | 김정욱 책임 | 15 | 14 | 30 | 25 | 0 | 0 | - | 0% | 0% | - | 45 | 39 | 86.67% | 30 | 15 | 50% | - | 30 | 25 | 83.33% | - | 20 | 5 | 25% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
13 | RPMB | 안병욱 선임 | 안병욱 선임 | 20 | 18 | 35 | 23 | 0 | 0 | - | 0% | 0% | - | 55 | 41 | 74.55% | 20 | 20 | 100% | - | 30 | 25 | 83.33% | - | 25 | 2 | 8% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
14 | Mail Box | 안병욱 선임 | 안병욱 선임 | 30 | 20 | 20 | 18 | 0 | 0 | - | 0% | 0% | - | 50 | 38 | 76% | 35 | 30 | 85.71% | - | 30 | 24 | 80% | - | 25 | 5 | 20% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
15 | Timer | 안병욱 선임 | 안병욱 선임 | 15 | 10 | 20 | 15 | 0 | 0 | - | 0% | 0% | - | 35 | 25 | 71.43% | 35 | 30 | 85.71% | - | 30 | 28 | 93.33% | - | 25 | 10 | 40% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
16 | WDT | 안병욱 선임 | 안병욱 선임 | 18 | 10 | 20 | 16 | 0 | 0 | - | 0% | 0% | - | 38 | 26 | 68.42% | 35 | 30 | 85.71% | - | 40 | 32 | 80% | - | 20 | 2 | 10% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
17 | UART | 안병욱 선임 | 안병욱 선임 | 17 | 15 | 25 | 20 | 0 | 0 | - | 0% | 0% | - | 42 | 35 | 83.33% | 25 | 30 | 120% | - | 25 | 20 | 80% | - | 30 | 2 | 6.667% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
18 | Clock Controller | 김정욱 책임 | 김정욱 책임 | 16 | 15 | 25 | 25 | 0 | 0 | - | 0% | 0% | - | 41 | 40 | 97.56% | 25 | 20 | 80% | - | 25 | 25 | 100% | - | 30 | 5 | 16.67% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
19 | Reset Controller | 김정욱 책임 | 김정욱 책임 | 20 | 13 | 25 | 22 | 0 | 0 | - | 0% | 0% | - | 45 | 35 | 77.78% | 25 | 20 | 80% | - | 25 | 22 | 88% | - | 30 | 8 | 26.67% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
20 | eFuse Controller | 안병욱 선임 | 안병욱 선임 | 21 | 20 | 25 | 22 | 0 | 0 | - | 0% | 0% | - | 46 | 42 | 91.3% | 40 | 35 | 87.5% | - | 25 | 22 | 88% | - | 25 | 9 | 36% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
21 | M-PHY | 이현주 선임 | 이현주 선임 | 25 | 22 | 25 | 23 | 0 | 0 | - | 0% | 0% | - | 50 | 45 | 90% | 40 | 30 | 75% | - | 25 | 23 | 92% | - | 25 | 7 | 28% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
22 | Nand PHY | 이종용 선임 | 이종용 선임 | 20 | 20 | 30 | 25 | 0 | 0 | - | 0% | 0% | - | 50 | 45 | 90% | 35 | 30 | 85.71% | - | 30 | 30 | 100% | - | 30 | 5 | 16.67% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
23 | Nand IO | 이종용 선임 | 이종용 선임 | 30 | 25 | 35 | 30 | 0 | 0 | - | 0% | 0% | - | 65 | 55 | 84.62% | 35 | 30 | 85.71% | - | 20 | 18 | 90% | - | 30 | 8 | 26.67% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
24 | Test Mux | 양창호 선임 | 양창호 선임 | 35 | 30 | 20 | 15 | 0 | 0 | - | 0% | 0% | - | 55 | 45 | 81.82% | 20 | 20 | 100% | - | 30 | 15 | 50% | - | 25 | 2 | 8% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
25 | HW Bypass | 양창호 선임 | 양창호 선임 | 20 | 20 | 25 | 25 | 0 | 0 | - | 0% | 0% | - | 45 | 45 | 100% | 25 | 20 | 80% | - | 25 | 5 | 20% | - | 30 | 2 | 6.667% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
26 | Analog IP | 양창호 선임 | 양창호 선임 | 20 | 18 | 30 | 30 | 0 | 0 | - | 0% | 0% | - | 50 | 48 | 96% | 30 | 20 | 66.67% | - | 30 | 2 | 6.667% | - | 40 | 5 | 12.5% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
27 | GPIO | 양창호 선임 | 양창호 선임 | 20 | 10 | 40 | 35 | 0 | 0 | - | 0% | 0% | - | 60 | 45 | 75% | 30 | 20 | 66.67% | - | 20 | 3 | 15% | - | 50 | 2 | 4% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
- | End to End | ALL | 조성엽 책임 | 10 | 5 | 10 | 0 | 0 | 0 | - | 0% | 0% | - | 20 | 5 | 25% | 25 | 15 | 60% | - | 25 | 5 | 20% | - | 20 | 5 | 25% | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
- | Post-Silicon Validation | ALL | ALL
Sub Average |  |  |  | 18.7143 | 14.6429 | 24 | 19.0357 | 0 | 0 |  | 0% | 0% |  | 42.7143 | 33.6786 |  | 30.3571 | 24.6786 | - |  | 26.4286 | 19.3571 | - |  | 26.6071 | 4.2143 | -
Sub Sum |  |  |  | 524 | 410 | 672 | 533 | 0 | 0 | 0% | - | - |  | 1196 | 943 |  | 850 | 691 | 81.29% |  | 740 | 542 | 73.24% |  | 745 | 118 | 15.84%
Total | [16 empty] | 1374 | 691 | 50.29%
100%
90%
70%
50%
0%
Formulas:
Last Updated = [1]Summary!$AA7
Note on N33: sycho: FPGA 환경에서의 test vector의 coverage 임
Note on N35: sycho: Cortex-M3는 제외

## Chart 2 - Data
Projecgt 별 Test Case 수 비교
| IP | Project A | Project B | Project C | Project D | Project E | Project G
1 | Cortex-M3 | 75 | 85 | 90 | 70 | 85 | 30
2 | HCT | 25 | 5 | 80 | 25 | 7 | 85
3 | FCT | 30 | 25 | 30 | 50 | 7 | 8
4 | Buffer Manager | 50 | 60 | 70 | 80 | 50 | 20
5 | Search Engine | 25 | 25 | 30 | 30 | 30 | 50
6 | MTSE
7 | System Memory
8 | Data Buffer
9 | DMA
10 | Back Bone
11 | System Controller
12 | PMU
13 | RPMB
14 | Mail Box
15 | Timer
16 | WDT
17 | UART
18 | Clock Controller
19 | Reset Controller
20 | eFuse Controller
21 | M-PHY
22 | Nand PHY
23 | Nand IO
24 | Test Mux
25 | HW Bypass
26 | Analog IP
27 | GPIO
- | End to End
- | Post-Silicon Validation
Sub Average
Sub Sum
Total |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Cover
SoC Design Verification Checklist
Template version 0.1
Approval
|  |  | Team / Name |  |  | UFS SoC / 홍길동 |  |  | Soc Architecture / 나도야 |  |  | UFS SoC / 독고탁
|  |  | e-mail |  |  | xxx.xxx@sk.com |  |  | xxx.xxx@sk.com |  |  | xxx.xxx@sk.com
|  |  | Phone |  |  | +82-01-5678-1234 |  |  | +82-01-5678-5678 |  |  | +82-01-5678-4321
○ Product
UFS2.0 G3X2L Armstrong
○ 작성목적
이 문서는 P4C Design 수행 시 RTL Design 담당자와 Design Verification 담당자들이 Tech bench를 통해 수행한 Design 검증 항목이 누락되지 않도록 하고, RTL Freeze의 판단 근거로 삼기 위한 목적으로 작성함
○ Audience
| Author | ◎ |  |  | Head | VPs | Arch. | SoC | FW | PE | AE | FPP | NAND | QRA
| Distribution | ○ |  | Bundang | ○ | ○ | ○ | ◎ | ○ | ○ | ○ | ○ |  | ○
| Not Involved |  |  | HMS
|  |  |  | FST |  |  |  | ○ | ○ | ○ | ○
|  |  |  | SFS |  |  |  | ○ | ○
3rd party
○ Document Revision History
| Version Number | Date |  |  | Author |  |  | Summary of Changes
| V1.0 | April 21th, 2015 |  |  | UFS SoC / 홍길동 |  |  | Published as Initial Draft Version
○ Flow and position of the report
Initial RTL Release
RTL Design
Design Verification
Design Verification Checklist
Deliverable
Work
Design Review
Complete RTL
Cadidate Release
Stable RTL
Cadidate Release
RTL Freeze
Cadidate Release
Design Verification
by Simulation
Design Verification
by Simulation
Design Verification
by Simulation
Design Verification
by Simulation

## VerificationStatusSummary
Columbus Verification Status Summary | [27 empty] | 2015-05-14
No. | IP | RTL Designer | Verification Engineer | RTL Sim. | [9 empty] | FPGA |  |  |  | POST Sim. |  |  |  | ASIC |  |  |  | Last Updated |  |  |  | Remark / Coverage Waive
|  |  |  | F1 |  | F2 |  | F3 |  | F1~3 | Cov. SoC (F2,F3) | Cov. S.A (F0,F1) | Done | Cases | Pass | Prog. | Done | Cases | Pass | Prog. | Done | Cases | Pass | Prog. | Done | Date | RTL | FPGA | ASIC
|  |  |  | Cases | Pass | Cases | Pass | Cases | Pass | Prog.
1 | Cortex-M3 | 최호윤 수석 | 조성엽 책임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
2 | HCT | 이원규 선임 | 박재우 책임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
3 | FCT | 천동엽 책임 | 조성엽 책임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
4 | Buffer Manager | 지대근 책임 | 조성엽 책임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
5 | Search Engine | 김현욱 선임 | 김현욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
6 | MTSE | 김현욱 선임 | 김현욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
7 | System Memory | 김현욱 선임 | 김현욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
8 | Data Buffer | 김현욱 선임 | 김현욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
9 | DMA | 김현욱 선임 | 김현욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
10 | Back Bone | 최호윤 수석 | 최호윤 수석 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
11 | System Controller | 김정욱 책임 | 김정욱 책임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
12 | PMU | 김정욱 책임 | 김정욱 책임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
13 | RPMB | 안병욱 선임 | 안병욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
14 | Mail Box | 안병욱 선임 | 안병욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
15 | Timer | 안병욱 선임 | 안병욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
16 | WDT | 안병욱 선임 | 안병욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
17 | UART | 안병욱 선임 | 안병욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
18 | Clock Controller | 김정욱 책임 | 김정욱 책임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
19 | Reset Controller | 김정욱 책임 | 김정욱 책임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
20 | eFuse Controller | 안병욱 선임 | 안병욱 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
21 | M-PHY | 이현주 선임 | 이현주 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
22 | Nand PHY | 이종용 선임 | 이종용 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
23 | Nand IO | 이종용 선임 | 이종용 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
24 | Test Mux | 양창호 선임 | 양창호 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
25 | HW Bypass | 양창호 선임 | 양창호 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
26 | Analog IP | 양창호 선임 | 양창호 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
27 | GPIO | 양창호 선임 | 양창호 선임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
- | End to End | ALL | 조성엽 책임 | 0 | 0 | 0 | 0 | 0 | 0 | - | 0% | 0% | - | 0 | 0 | - | - | 0 | 0 | - | - | 0 | 0 | - | - | 2015-05-14 | ? | ? | ? | RTL: POST: FPGA:
- | Post-Silicon Validation | ALL | ALL
Sub Average |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% |  | 0 | 0 | - |  | 0 | 0 | - |  | 0 | 0 | -
Sub Sum |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - |  | 0 | 0 | - |  | 0 | 0 | - |  | 0 | 0 | -
Total | [13 empty] | 0 | 0 | -
100%
90%
70%
50%
0%
Formulas:
Last Updated = [1]Summary!$AA7
Note on N33: sycho: FPGA 환경에서의 test vector의 coverage 임
Note on N35: sycho: Cortex-M3는 제외

## VerificationStatusHistory
Armstrong Verification Summary History
Date | RTL Sim. | [5 empty] | FPGA |  |  |  | POST Sim. |  |  |  | ASIC
| Cases | Pass | Prog. | Cov. SoC (F2,F3) | Cov. S.A (F0,F1) | Done | Cases | Pass | Prog. | Done | Cases | Pass | Prog. | Done | Cases | Pass | Prog. | Done

## Table
|  | test category | [19 empty] | test level
|  | RTL |  |  |  |  | FPGA |  |  |  |  | POST |  |  |  |  | ASIC
|  | Sanity Test | Function Test | Comprehensive Test | Performance & Regression Test | Specific & Etc. Test | Sanity Test | Function Test | Comprehensive Test | Performance & Regression Test | Specific & Etc. Test | Sanity Test | Function Test | Comprehensive Test | Performance & Regression Test | Specific & Etc. Test | Sanity Test | Function Test | Comprehensive Test | Performance & Regression Test | Specific & Etc. Test | etc. | F0 | F1 | F1_all | F2_all | F3 | F3_all | FPGA | ASIC
1 | ARC-EM4 | 9 | 13 | 0 | 0 | 0 | 6 | 18 | 1 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 5 | 17 | 10 | 0 | 0 | 2 | 0 | 3 | 3 | 16 | 2 | 0 | 8 | 9
2 | NFC | 202 | 54 | 57 | 4 | 0 | 3 | 54 | 54 | 20 | 5 | 1 | 25 | 0 | 0 | 0 | 0 | 57 | 59 | 9 | 0 | 1 | 204 | 0 | 100 | 15 | 5 | 0 | 26 | 0
3 | ECC | 1 | 50 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 50 | 0 | 2 | 0 | 0 | 0 | 0 | 0
4 | CDE | 6 | 7 | 8 | 0 | 0 | 5 | 7 | 13 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 7 | 13 | 0 | 0 | 1 | 0 | 0 | 10 | 14 | 1 | 0 | 0 | 0
5 | Boost Engine | 4 | 6 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 2 | 2 | 4 | 1 | 0 | 0 | 0
6 | UFS | 194 | 56 | 0 | 7 | 0 | 14 | 0 | 27 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 193 | 1 | 75 | 5 | 0 | 42 | 0
7 | AES-UFS | 4 | 19 | 12 | 0 | 0 | 3 | 13 | 7 | 1 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 17 | 12 | 1 | 0 | 65 | 0
8 | AES-LB | 4 | 21 | 8 | 5 | 0 | 3 | 14 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 7 | 22 | 2 | 1 | 0 | 5 | 0
9 | MACC | 5 | 5 | 28 | 1 | 0 | 3 | 5 | 17 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 5 | 17 | 0 | 0 | 1 | 0 | 0 | 18 | 18 | 2 | 0 | 0 | 0
10 | Backbone | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0
11 | Buffer Manager | 4 | 27 | 26 | 0 | 0 | 3 | 7 | 19 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 3 | 4 | 5 | 0 | 0 | 1 | 0 | 27 | 7 | 16 | 3 | 4 | 0 | 0
12 | System Memory | 2 | 39 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0
13 | Data Buffer | 2 | 40 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0
14 | AMP | 4 | 88 | 7 | 0 | 0 | 3 | 58 | 7 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 42 | 35 | 13 | 8 | 0 | 0 | 0
15 | MTSE | 4 | 35 | 1 | 14 | 0 | 3 | 28 | 1 | 14 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 28 | 1 | 14 | 0 | 1 | 0 | 8 | 42 | 1 | 2 | 0 | 1 | 0
16 | Mail Box | 5 | 51 | 0 | 2 | 5 | 4 | 51 | 0 | 0 | 5 | 1 | 5 | 0 | 0 | 0 | 4 | 51 | 0 | 0 | 0 | 1 | 0 | 2 | 5 | 0 | 55 | 0 | 0 | 0
17 | Timer | 4 | 8 | 5 | 0 | 0 | 3 | 8 | 5 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 13 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 13 | 0 | 0
18 | UART | 10 | 17 | 0 | 0 | 0 | 9 | 15 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 15 | 0 | 0 | 0 | 1 | 0 | 0 | 21 | 4 | 1 | 0 | 0 | 0
19 | GPIO | 6 | 8 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 0 | 3 | 0 | 0 | 11 | 1 | 1 | 0 | 0 | 0
20 | System Register | 4 | 158 | 0 | 0 | 0 | 2 | 13 | 0 | 0 | 0 | 2 | 57 | 0 | 0 | 0 | 1 | 39 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 164 | 0 | 0 | 0
21 | PMU | 1 | 35 | 32 | 0 | 4 | 0 | 4 | 19 | 4 | 1 | 0 | 20 | 0 | 0 | 0 | 0 | 21 | 37 | 6 | 2 | 1 | 0 | 2 | 2 | 1 | 37 | 39 | 9 | 0
22 | Clock Controller | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
23 | Reset Controller | 2 | 10 | 0 | 0 | 0 | 1 | 9 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 1 | 0 | 0 | 4 | 0 | 12 | 1 | 0 | 0
24 | M-PHY | 6 | 32 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 6 | 13 | 0 | 0 | 0 | 6 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 2 | 18
25 | Nand PHY | 0 | 33 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0
26 | NAND IO | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 6 | 0 | 0
27 | Test IO Mux | 1 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0
28 | eFuse Controller | 6 | 1 | 2 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 1 | 1 | 2 | 4 | 0 | 0
29 | HW Bypass | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 16 | 0 | 0
30 | Analog IP | 0 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 22 | 0 | 0
31 | Token Generator | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0
31 | Host Interaction (Sonic) | 0 | 0 | 0 | 0 | 0 | 21 | 315 | 25 | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 20 | 312 | 35 | 5 | 18 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 2
Total |  | 496 | 934 | 212 | 33 | 9 | 97 | 664 | 206 | 48 | 89 | 18 | 246 | 9 | 0 | 0 | 65 | 675 | 183 | 34 | 20 | 43 | 254 | 387 | 360 | 195 | 406 | 105 | 254 | 29
Note on X4: sycho: N/A -> etc.

## ValidationStatusSummary
TBD

## ValidationStatusHistory
TBD

## Doc.revision
document revision history
rev | date | description | author
0.1 | 2014-04-29 | 양식 초안 작성 | 조성엽

## 임시_Summary(v1)
Armstrong Verification Check List Summary
last updated: |  | 2014-04-04
No. | IP | RTL Designer | Verification Engineer | Simulation Verification | [9 empty] | FPGA Verification |  |  |  | Last Updated |  | Remark / Coverage Waive
|  |  |  | RTL | [5 empty] | POST | [7 empty] | RTL | FPGA
|  |  |  | Cases | Pass | Prog | Coverage SoC(F2,F3) | Coverage S.A(F0,F1) | Done | Cases | Pass | Prog | Done | Cases | Pass | Prog | Done | REV01 | dd79
1 | ARC-EM4 | 박재한 책임 | 조성엽 책임 | 19 | 19 | 100% | 37% | N/A | - | 0 | 0 | - | - | 25 | 23 | 92% | - | REV01 |  | RTL: POST: FPGA:
2 | NFC | 김재우 책임 | 윤동준 선임 | 242 | 242 | 100% | N/A | 98% | - | 0 | 0 | - | - | 130 | 126 | 96.92% | - | REV01 | XXXX | RTL: Line coverage report(use tool : VCS) - F2/F3 coverage의 경우 F0/F1 coverage에서 이미 모든 경우가 반영 되어 있으므로 추출 의미가 없음 POST: FPGA:
3 | ECC | 김주희 선임 | 조성근 선임 | 51 | 51 | 100% | N/A | 90% | - | 0 | 0 | - | - | N/A | N/A | N/A | - | REV01 | XXXX | RTL: VCS line coverage 결과 POST: NFC에 포함 FPGA: NFC에 포함
4 | CDE | 이학대 책임 | 윤동준 선임 | 26 | 26 | 100% | 99% | 99% | - | 0 | 0 | - | - | 25 | 25 | 100% | - | REV01 | d040 | RTL: POST: FPGA:
5 | Boost Engine | 조성근 선임 | 조성근 선임 | 8 | 8 | 100% | 83% | 97% | - | 0 | 0 | - | - | 4 | 4 | 100% | - | REV01 | XXXX | RTL: POST: FPGA:
6 | UFS | 박재우 선임 | 조성엽 책임 | 212 | 207 | 97.64% | 73% | 73% | - | 0 | 0 | - | - | 43 | 26 | 60.47% | - | REV01 | XXXX | RTL: 현재 Design 수정 중이기에 code merge 불가 따라서 현재 coverage는 단일 random constaint simulation code coverage 결과 1/24 design 완료 후 1/28내에 all test pass 된 coverage 공유 예정 POST: FPGA:
7 | AES-UFS | 박재한 책임 | 조성엽 책임 | 34 | 34 | 100% | 95% | 95% | - | 0 | 0 | - | - | 82 | 81 | 98.78% | - | REV01 | XXXX | RTL: POST: FPGA:
8 | AES-LB | 이현주 선임 | 이현주 선임 | 37 | 37 | 100% | 96% | 96% | - | 0 | 0 | - | - | 30 | 30 | 100% | - | REV01 | d040 | RTL: POST: FPGA: F3에서 ISR을 수행하여 F1과 merge한 결과임
9 | MACC | 안병욱 선임 | 이현주 선임 | 33 | 33 | 100% | 92.91% | 92% | - | 0 | 0 | - | - | 25 | 25 | 100% | - | REV01 | D052 | RTL: POST: FPGA:
10 | Backbone | 이학대 책임 | 이학대 책임 | 5 | 5 | 100% | 92.53% | 92.53% | - | 0 | 0 | - | - | N/A | N/A | N/A | - | REV01 | d040 | RTL: POST: FPGA: Master/Slave IP들의 동작검증으로 대체함
11 | Buffer Manager | 송광종 책임 | 조성엽 책임 | 48 | 48 | 100% | 96.35% | 96.35% | - | 0 | 0 | - | - | 22 | 22 | 100% | - | REV01 | d076 | RTL: POST: FPGA:
12 | System Memory | 박승진 책임 | 박승진 책임 | 41 | 41 | 100% | 97% | 97% | - | 0 | 0 | - | - | 3 | 3 | 100% | - | REV01 | XXXX | RTL: POST: FPGA: Unipro/NFC/AMP/BM test에서 사용 되므로, CPU가 full range를 byte/half-word/word 단위로 SCAN 하는 테스트만 진행 하기로 결정 됨
13 | Data Buffer | 박승진 책임 | 박승진 책임 | 42 | 42 | 100% | 97% | 97% | - | 0 | 0 | - | - | 3 | 3 | 100% | - | REV01 | XXXX | RTL: POST: FPGA: Unipro/NFC/AMP test에서 사용되기 때문에, CPU가 full range를 byte/half-word/word 단위로 scan 하는 테스트만 진행 하기로 결정 됨
14 | AMP | 박승진 책임 | 정재형 책임 | 68 | 68 | 100% | 98% | 98% | - | 0 | 0 | - | - | 68 | 68 | 100% | - | REV01 | XXXX | RTL: POST: FPGA:
15 | MTSE | 송광종 책임 | 이현주 선임 | 49 | 49 | 100% | 99.7% | 99.7% | - | 0 | 0 | - | - | 41 | 41 | 100% | - | REV01 | d053 | RTL: POST: FPGA:
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | Timer | 이종용 선임 | 윤동준 선임 | 15 | 15 | 100% | 93.77% | 86.9% | - | 2 | #REF! | #REF! | - | 15 | 15 | 100% | - | REV01 | XXXX | RTL: POST: FPGA:
18 | UART | 이종용 선임 | 윤동준 선임 | 27 | 27 | 100% | N/A | N/A | - | 1 | #REF! | #REF! | - | 24 | 24 | 100% | - | REV01 | XXXX | RTL: 도입 IP 로 netlist model 이기에 RTL coverage 측정이 realistic 하지 않음.
19 | GPIO | 이종용 선임 | 조성엽 책임 | 14 | 14 | 100% | N/A | N/A | - | 1 | #REF! | #REF! | - | 15 | #REF! | #REF! | - | REV01 | XXXX | RTL: 도입 IP로 netlist model이기에 RTL coverage 측정이 realistic 하지 않음.
20 | System Register | 지미옥 책임 | 지미옥 책임 | 84 | 84 | 100% | 82% | 80% | - | 0 | 0 | - | - | 7 | 6 | 85.71% | - | REV01 | XXXX | RTL: control register 들로 이루어져, coverage 가 낮음. POST: FPGA: Register Read Write test 만 가능
21 | PMU | 지미옥 책임 | 정재형 책임 | 94 | 77 | 81.91% | 92% | 91% | - | 0 | 0 | - | - | 48 | 25 | 52.08% | - | REV01 | dd79 | RTL: F3 진행 중. POST: FPGA:
22 | Clock Con | 지미옥 책임 | 지미옥 책임 | 11 | 11 | 100% | 91% | 91% | - | 0 | 0 | - | - | N/A | N/A | N/A | - | REV01 | XXXX | RTL: POST: FPGA: test 불가능
23 | Reset Con | 지미옥 책임 | 지미옥 책임 | 14 | 14 | 100% | 83% | 81% | - | 0 | 0 | - | - | 6 | 5 | 83.33% | - | REV01 | XXXX | RTL: 1) F1/F3 coverage : test mode 가 off 되어있어, coverage 에 반영 안됨. (test mode 는 test coverage 로 check 됨.) POST: FPGA:
24 | M-PHY | 김현욱 선임 | 김현욱 선임 | 30 | 26 | 86.67% | N/A | N/A | - | 0 | 0 | - | - | N/A | N/A | N/A | - | REV01 | XXXX | RTL: POST: FPGA:
25 | Nand PHY | 천동엽 선임 | 천동엽 선임 | 5 | 5 | 100% | N/A | N/A | - | 0 | 0 | - | - | N/A | N/A | N/A | - | REV01 | XXXX | RTL: POST: FPGA:
26 | ONFI IO | 안레센 선임 | 안레센 선임 | 7 | 7 | 100% | 72% | 72% | - | 0 | 0 | - | - | N/A | N/A | N/A | - | REV01 | XXXX | IO 계약이 진행 중 / 추후 update하겠음 RTL: POST: FPGA:
27 | Test IO Mux | 이광순 선임 | 이광순 선임 | 14 | 14 | 100% | N/A | 88% | - | 0 | 0 | - | - | N/A | N/A | N/A | - | REV01 | XXXX | RTL: coverage -> expression 기준 POST: FPGA: N/A
28 | eFuse Con | 박재한 책임 | 박재한 책임 | 10 | 10 | 100% | 95% | 95% | - | 3 | 0 | 0% | - | 5 | 5 | 100% | - | REV01 | XXXX | RTL: POST: FPGA:
29 | HW Bypass | 안영규 책임 | 이광순 선임 | 47 | 47 | 100% | N/A | N/A | - | 0 | 0 | - | - | N/A | N/A | N/A | - | REV01 | XXXX | RTL: POST: FPGA:
30 | Analog IP | 양창호 선임 | 양창호 선임 | 21 | 19 | 90.48% | N/A | N/A | - | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | REV01 | XXXX | RTL: POST: FPGA:
31 | Token Gen | 안레센 선임 | 안레센 선임 | 8 | 8 | 100% | 72% | 72% | - | 0 | 0 | - | - | N/A | N/A | N/A | O | REV01 | XXXX | RTL: POST: FPGA:
Sub Sum |  |  |  | #REF! | #REF! | - | - | - |  | #REF! | #REF! | - | - | #REF! | #REF! | -
Sub Average |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
Total Item/Progress/Coverage |  |  |  | #REF! |  | #REF! |  | #REF!
| 해당 항목 완료 | 100%
90%
N/A | 해당 사항 없음 | 70%
50%
0%
Reference

## 임시_history(v1)
Armstrong Verification Summary History
Date | Simulation Verification | [9 empty] | FPGA Verification |  |  |  | Remark
| RTL | [5 empty] | POST
| Cases | Pass | Prog | Coverage SoC / S.A |  | Done | Cases | Pass | Prog | Done | Cases | Pass | Prog | Done
2013-09-16 | 21.1935 | 3.8387 | 4.288% | 0% | 0% |  | 0 | 0 | 0% |  | 11.7742 | 0 | 0% |  | draft version
2013-10-01 | 21.1935 | 3.8387 | 4.288% | 0% | 0% |  | 0 | 0 | 0% |  | 11.7742 | 0 | 0%
2013-10-21 | 24.6129 | 7.871 | 35.37% | 0% | 11.03% |  | 0 | 0 | 0% |  | 12.0968 | 0 | 0%
2013-10-27 | 25.1935 | 8.5161 | 42.03% | 0% | 12.77% |  | 0 | 0 | 0% |  | 12.0968 | 0 | 0%
2013-11-04 | 25.7419 | 13.3548 | 51.09% | 0% | 21.1% |  | 0 | 0 | 0% |  | 11.7742 | 0 | 0%
2013-11-08 | 30.7419 | 17.9677 | 57.7% | 2.774% | 39.94% |  | 0 | 0 | 0% |  | 11.871 | 0 | 0%
2013-11-11 | 31.0645 | 18.3226 | 58.47% | 2.774% | 47.87% |  | 0 | 0 | 0% |  | 11.871 | 0 | 0%
2013-11-18 | 31.129 | 19.5806 | 63% | 2.774% | 50.03% |  | 0 | 0 | 0% |  | 12.2581 | 0.12903 | 3.704%
2013-11-25 | 31.6452 | 20.0323 | 63.86% | 2.774% | 50.03% |  | 0 | 0 | 0% |  | 15.3226 | 1.6774 | 8.386%
2013-11-26 | 32.129 | 19.7097 | 63.67% | 2.774% | 50.03% |  | 0 | 0 | 0% |  | 16.2258 | 2.4516 | 15.24%
2013-11-29 | 31.9355 | 20.5161 | 67.06% | 2.774% | 47.43% |  | 0 | 0 | 0% |  | 15.5484 | 2.5161 | 13.9%
2013-12-02 | 31.9677 | 20.8065 | 67.29% | 2.774% | 47.43% |  | 0 | 0 | 0% |  | 15.7097 | 3.0968 | 15.43%
2013-12-05 | 34.1935 | 24.3226 | 58.81% | 2.774% | 47.43% |  | 0.096774 | 0 | 0% |  | 16.2581 | 3.4194 | 13.94%
2013-12-09 | 34.6452 | 24.6129 | 57.8% | 2.774% | 48.87% |  | 0.096774 | 0 | 0% |  | 17.1667 | 4.1667 | 20.86%
2013-12-10 | 35.1613 | 24.6129 | 56.7% | 2.774% | 48.42% |  | 0.096774 | 0 | 0% |  | 17.6667 | 4.1667 | 19.47%
2013-12-23 | 35.5806 | 26.871 | 60.03% | 2.774% | 48.42% |  | 0.096774 | 0 | 0% |  | 18.6 | 6.0667 | 25.75%
2013-12-30 | 35.9355 | 27.4839 | 64.43% | 2.774% | 51.32% |  | 0.096774 | 0 | 0% |  | 18.8333 | 6.1667 | 26.52%
2014-01-06 | 36.5161 | 28.129 | 64.25% | 2.774% | 51.92% |  | 0.096774 | 0 | 0% |  | 19.6333 | 7.8333 | 36.77%
2014-01-07 | 38.3 | 34.1667 | 84.62% | 6.036% | 59.13% |  | 0.1 | 0 | 0% |  | 23.7407 | 11.4074 | 58.25%
2014-01-09 | 38.9 | 35.3333 | 88.82% | 16.07% | 72.75% |  | 0.1 | 0 | 0% |  | 25.6 | 12.2 | 55.1%
2014-01-13 | 38.9333 | 36.5667 | 91.1% | 46.81% | 76.41% |  | 0.1 | 0 | 0% |  | 30.9524 | 14.619 | 55.99%
2014-01-14 | 39.0667 | 36.9333 | 91.82% | 75.85% | 82.18% |  | 0.1 | 0 | 0% |  | 30.9524 | 15 | 58.07%
2014-01-20 | 39.3 | 37.2 | 91.87% | 82.68% | 83.82% |  | 0.1 | 0 | 0% |  | 31.65 | 16.5 | 59.41%
2014-01-21 | 39.4333 | 37.3333 | 93.1% | 86.62% | 87.17% |  | 0.1 | 0 | 0% |  | 33.4737 | 17.6842 | 66.69%
2014-01-23 | 41.3 | 38.6 | 94% | 90.03% | 90.02% |  | 0.1 | 0 | 0% |  | 25.0526 | 20.8947 | 72.49%
2014-02-04 | 41.6333 | 38.9667 | 93.86% | 90.03% | 90.02% |  | 0.1 | 0 | 0% |  | 25.4737 | 21.9474 | 86.76%
2014-02-06 | 41.7667 | 39.5 | 94.5% | 90.03% | 90.02% |  | 0.1 | 0 | 0% |  | 25.6316 | 23.7895 | 89.38%
2014-02-11 | 42.8667 | 40.4667 | 94.58% | 90.03% | 90.02% |  | 0.1 | 0 | 0% |  | 28.8421 | 27 | 90.26%
2014-02-18 | 43.3333 | 40.9 | 95.57% | 90.03% | 90.02% |  | 0.1 | 0 | 0% |  | 31.1053 | 27.8421 | 91.73%
2014-02-21 | 43.3333 | 41.0333 | 96.2% | 90.03% | 90.02% |  | 0.1 | 0 | 0% |  | 31.1053 | 27.8421 | 91.73%
2014-02-25 | 43.3667 | 41.2667 | 96.5% | 90.27% | 90.22% |  | 0.1 | 0 | 0% |  | 32.4211 | 28.8947 | 92.68%
2014-02-28 | 43.4333 | 41.4 | 96.71% | 90.27% | 90.22% |  | 0.1 | 0 | 0% |  | 32.2632 | 29.2105 | 93.23%
2014-03-06 | 43.4 | 41.6333 | 98.16% | 90.27% | 86.54% |  | 0.10345 | 0 | 0% |  | 31.4211 | 29.6842 | 95.01%
2014-03-12 | 44.4667 | 42.3 | 98.07% | 90.27% | 90.14% |  | 0.10345 | 0 | 0% |  | 31.3684 | 29.6842 | 95.06%
2014-03-14 | 44.3 | 41.7 | 97.39% | 90.27% | 90.14% |  | 0.10345 | 0 | 0% |  | 32.2 | 29.45 | 92.91%
2014-03-21 | 44.6333 | 42.5 | 98.01% | 90.27% | 90.14% |  | 0.10345 | 0 | 0% |  | 32.25 | 29.85 | 93.79%
2014-03-21 | 44.6333 | 42.5667 | 98.08% | 90.27% | 90.14% |  | 0.10345 | 0 | 0% |  | 32.25 | 29.85 | 93.79%
2014-04-04 | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF!
Reference
Reference